## Read Me
Eschool - Functional Test Plan
Scope: everything built so far (Oct 2026 build, includes Admissions 'pick an existing parent')
Purpose | Manual functional test of the completed modules. Work through the 'Test Cases' sheet top to bottom; each row is one check.
Modules covered | Login & Layout, Reusable Components, Class Sections, Subjects, Teachers, Parents, Admissions (incl. existing-parent picker), Students, Attendance, Documents, Users & Staff, Roles & Permissions, My Account, School Settings, Dashboard, role-based access, end-to-end flows, non-functional checks.
NOT in scope | Modules not built yet (Reports, Timetable, Fees, Exams, Results, Library, Notices, PTM, Calendar, Transport, Helpdesk, etc.): the sidebar items open the dashboard on purpose. Student / Parent portal logins are not built.
Environment | Web app: http://localhost:5173 - API: https://localhost:7100 - use a TEST database, never real data. Keep browser DevTools open (Console + Network): any red console error or HTTP 500 is a defect on its own.
Test data | All test records should start with 'ZT' (e.g. 'ZT Class A') so they are easy to find and delete. See sheet 'Test Data' for the users to create and sample values.
How to execute | 1) Filter 'Test Cases' by Module (use the filter arrows in row 1). 2) Do the steps. 3) Fill the yellow columns: Actual Result (only when different or useful), Status, Tested By, Date, Defect ID, Comments. 4) For every Fail, add a row in 'Defect Log' and put its ID in the test row.
Status values | Not Run (default) ¦ Pass ¦ Fail ¦ Blocked (cannot test because of another defect) ¦ N/A (not applicable)
Type / Priority | Type: Functional, Validation (bad input), Negative (should be refused), Security (permissions / data exposure), UI, Exploratory (the correct behaviour is not fixed: describe what you see). Priority: High = core flow or security, run first; Medium; Low.
Roles | Cases name the role to log in as. Admin sees everything. Clerk, Supervisor and Teacher are limited roles (create them in Users & Staff; see 'Test Data'). 'Role without X' means create a custom role in Roles & Permissions that lacks permission X.
Known limitations | 1) Attendance 'today' currently follows UTC, so between 00:00 and 04:00 Abu Dhabi time it can show yesterday (fix planned: F2). 2) Parent e-mail uniqueness is not enforced (PAR-14). 3) Lists load fully (no server paging yet): expect slowness only at very large volumes. 4) Fee, report-card and attendance-report buttons on students show 'not yet available'.
Summary | The 'Summary' sheet counts results automatically from the Status column. Do not type in it.
Colour key
Yellow cells | You fill these in (Actual Result, Status, Tested By, Date, Defect ID, Comments).
Status colours | Pass = green, Fail = red, Blocked = orange, Not Run = grey (automatic).

## Summary
Test Execution Summary
Calculated automatically from the Status column of 'Test Cases'.
Module | Total | Pass | Fail | Blocked | N/A | Not Run | % Executed | % Pass (of executed)
Login & Layout | 26 | 0 | 0 | 0 | 0 | 26 | 0% | 0%
Reusable Components | 12 | 0 | 0 | 0 | 0 | 12 | 0% | 0%
Class Sections | 15 | 0 | 0 | 0 | 0 | 15 | 0% | 0%
Subjects | 11 | 0 | 0 | 0 | 0 | 11 | 0% | 0%
Teachers | 18 | 0 | 0 | 0 | 0 | 18 | 0% | 0%
Parents | 19 | 0 | 0 | 0 | 0 | 19 | 0% | 0%
Admissions | 60 | 0 | 0 | 0 | 0 | 60 | 0% | 0%
Students | 45 | 0 | 0 | 0 | 0 | 45 | 0% | 0%
Attendance | 26 | 0 | 0 | 0 | 0 | 26 | 0% | 0%
Documents | 23 | 0 | 0 | 0 | 0 | 23 | 0% | 0%
Users & Staff | 23 | 0 | 0 | 0 | 0 | 23 | 0% | 0%
Roles & Permissions | 11 | 0 | 0 | 0 | 0 | 11 | 0% | 0%
My Account | 9 | 0 | 0 | 0 | 0 | 9 | 0% | 0%
School Settings | 9 | 0 | 0 | 0 | 0 | 9 | 0% | 0%
Dashboard | 1 | 0 | 0 | 0 | 0 | 1 | 0% | 0%
Roles & Access (RBAC) | 8 | 0 | 0 | 0 | 0 | 8 | 0% | 0%
End-to-End | 11 | 0 | 0 | 0 | 0 | 11 | 0% | 0%
Non-functional | 8 | 0 | 0 | 0 | 0 | 8 | 0% | 0%
TOTAL | 335 | 0 | 0 | 0 | 0 | 335 | 0% | 0%
High-priority cases
High priority total | 177
High priority failed | 0
High priority not yet run | 177
Open defects (Defect Log)
Open (New, In Progress, Reopened, Retest Failed) | 0
Critical / High severity still open | 0

## Test Cases
Test ID | Module | Feature / Area | Type | Priority | Log in as | Preconditions / Data | Steps | Expected Result | Actual Result | Status | Tested By | Date Tested | Defect ID | Comments
LOG-01 | Login & Layout | Access control | Negative | High | None | Logged out | Open the app root URL | Redirected to the login page |  | Not Run
LOG-02 | Login & Layout | Access control | Negative | High | None | Logged out | Open /students directly | Redirected to the login page; no student data visible |  | Not Run
LOG-03 | Login & Layout | Login | Functional | High | Admin | Valid Admin account | Enter username + correct password, Sign in | Dashboard opens; header shows 'Welcome, <username>' |  | Not Run
LOG-04 | Login & Layout | Login | Functional | Medium | Admin | Valid Admin account | Log in using the e-mail address instead of the username | Login works |  | Not Run
LOG-05 | Login & Layout | Login | Negative | High | None |  | Enter a wrong password | Message 'Invalid username/email or password.'; stays on login; button usable again |  | Not Run
LOG-06 | Login & Layout | Login | Validation | Medium | None |  | Submit the empty form | Fields flagged / message shown; no crash |  | Not Run
LOG-07 | Login & Layout | Login | UI | Low | None |  | Click Sign in twice quickly | Button disabled while submitting; only one request sent |  | Not Run
LOG-08 | Login & Layout | Session | Functional | High | Admin | Logged in | Refresh the browser page | Still logged in |  | Not Run
LOG-09 | Login & Layout | Session | Negative | Medium | Admin | Logged in | Clear the saved session (browser storage) and navigate to any page | Redirected to login |  | Not Run
LOG-10 | Login & Layout | Session | Negative | Medium | Admin | Logged in | Let the session expire (or edit expiry to the past in storage) and reload | Session cleared and login shown |  | Not Run
LOG-11 | Login & Layout | Session | Negative | Medium | Admin | Logged in | Tamper with the saved token, then open any list | App redirects to login automatically |  | Not Run
LOG-12 | Login & Layout | Session | Functional | High | Admin | Logged in | Click Logout in the sidebar, then press the browser Back button | Back at login; Back button does not show protected pages |  | Not Run
LOG-13 | Login & Layout | Login | Security | High | Any | Account with a few wrong attempts | Enter the wrong password repeatedly (about 5 times) for one account | Account becomes locked with a clear message; correct password is refused until an Admin unlocks (see USR-15) |  | Not Run
LOG-14 | Login & Layout | Login | Security | High | Any | User whose status is Inactive or Suspended | Try to log in | Login refused with a clear message |  | Not Run
LOG-15 | Login & Layout | Login | Functional | High | Any | User created by Admin (MustChangePassword) | Log in with the temporary password | Forced to the Change Password page; no other page is reachable until the password is changed |  | Not Run
LAY-01 | Login & Layout | Layout | UI | Medium | Admin | Logged in | Look at the sidebar | Sections visible (Overview, Records, Daily, ...); current page highlighted |  | Not Run
LAY-02 | Login & Layout | Layout | Functional | High | Admin | Logged in | Click each built item: Dashboard, Admissions, Students, Classes & Sections, Parents, Subjects, Teachers, Attendance, Documents, Users & Staff, Roles & Permissions, My Account, Settings | Correct page opens; URL changes |  | Not Run
LAY-03 | Login & Layout | Layout | Functional | Low | Admin | Logged in | Click a module that is not built yet (e.g. Reports, Timetable, Fees) | Redirects to the dashboard with no error (known placeholder) |  | Not Run
LAY-04 | Login & Layout | Layout | UI | Low | Admin | Logged in | Toggle dark mode on several pages, refresh | Theme switches, all pages readable in both themes, choice survives refresh |  | Not Run
LAY-05 | Login & Layout | Layout | UI | Medium | Admin | Logged in | Narrow the window to phone width | Layout usable; tables scroll horizontally; modals not clipped |  | Not Run
LAY-06 | Login & Layout | Layout | Negative | Low | Admin | Logged in | Open an unknown URL such as /xyz | Redirected to the dashboard |  | Not Run
LAY-07 | Login & Layout | Layout | Functional | Medium | Admin | Logged in | Check the top bar | School name from Settings is shown (and updates after it is changed in Settings) |  | Not Run
LAY-08 | Login & Layout | Layout | Security | High | Clerk | Clerk logged in | Look at the sidebar and try URLs of pages the role may not use (e.g. /roles-permissions, /settings) | Items the user may not use are hidden or the page shows a clear 'no permission' state; no data from the page is shown |  | Not Run
CMP-01 | Reusable Components | Validation modal | UI | High | Any |  | Trigger a server validation error on any form | Modal lists every server message; closes with button / X; no raw JSON shown |  | Not Run
CMP-02 | Reusable Components | Validation modal | UI | High | Any |  | Trigger a business-rule error (e.g. class is full) | Server message shown clearly (e.g. 'is full (1/1)') |  | Not Run
CMP-03 | Reusable Components | Confirm dialog | Functional | High | Any |  | Open any delete confirmation; Cancel, then repeat and Confirm | Cancel keeps data; Confirm does the action exactly once |  | Not Run
CMP-04 | Reusable Components | Details modal | UI | Medium | Any |  | Open any View (eye) modal | All sections shown; empty values show a dash; closes cleanly |  | Not Run
CMP-05 | Reusable Components | Table footer / paging | Functional | High | Any | List with >25 rows | Check footer text; change page size 10/25/50; use Prev/Next | 'Showing x-y of N' correct; page size changes rows; Prev/Next disabled at the ends |  | Not Run
CMP-06 | Reusable Components | Quick search | Functional | Medium | Any |  | Type in the search box above a table | Rows filter live; paging resets to page 1 |  | Not Run
CMP-07 | Reusable Components | Export CSV | Functional | Medium | Any |  | Filter a list, click Export CSV, open in Excel | File downloads; header + rows match what is filtered on screen; special characters/commas not broken |  | Not Run
CMP-08 | Reusable Components | Modals | UI | Low | Any |  | Open a modal; press Esc; scroll the page behind | Esc/X closes where supported; background does not scroll; focus lands in first field |  | Not Run
CMP-09 | Reusable Components | Error state | Negative | Medium | Any | API stopped | Open a list page while the API is down | Error message or error state; not a blank page or endless spinner |  | Not Run
CMP-10 | Reusable Components | Toasts | UI | Low | Any |  | Save something successfully; also cause an error | Success/error toast appears and disappears; text is understandable |  | Not Run
CLS-01 | Class Sections | List | Functional | High | Admin | Logged in | Open Classes & Sections | List loads; Academic Year, Section, Stage, Medium filters are populated |  | Not Run
CLS-02 | Class Sections | Create | Validation | High | Admin |  | Click Add Class, leave all empty, Save | Required-field messages; nothing created |  | Not Run
CLS-03 | Class Sections | Create | Functional | High | Admin |  | Add Name 'ZT Class', Section 'A', Stage Primary, Medium English, Stream General, Capacity 30 | Created; appears with display name like 'ZT Class A (2026-2027)'; code auto-generated |  | Not Run
CLS-04 | Class Sections | Create | Negative | High | Admin | ZT Class A exists | Add the same class again | Error about duplicate; nothing created |  | Not Run
CLS-05 | Class Sections | Create | Validation | Medium | Admin |  | Capacity 0 and 201; Grade 13; Floor 21 | Each gives a validation message |  | Not Run
CLS-06 | Class Sections | Create | Functional | Low | Admin |  | Leave Grade blank (LKG/UKG case) | Accepted |  | Not Run
CLS-07 | Class Sections | Edit | Functional | Medium | Admin |  | Edit a class, change Room, Save | Saved; reflected in the list |  | Not Run
CLS-08 | Class Sections | Edit | Negative | High | Admin | Class with students | Lower capacity below current student count | Error 'Capacity cannot be lower than the current strength' |  | Not Run
CLS-09 | Class Sections | Status | Functional | High | Admin |  | Set the class Inactive | Row shows Inactive; class no longer appears in admission / student / enrol class lists |  | Not Run
CLS-10 | Class Sections | View | UI | Low | Admin |  | Click View (eye) | Details show enrolled count and teacher info |  | Not Run
CLS-11 | Class Sections | Filters | Functional | Medium | Admin |  | Use each filter and the search, then combine, then clear | Lists narrow correctly; combining works; clearing restores all |  | Not Run
CLS-12 | Class Sections | Delete | Functional | Medium | Admin | Empty class | Delete the class | Confirm dialog, then row disappears |  | Not Run
CLS-13 | Class Sections | Delete | Negative | High | Admin | Class with students/subjects | Delete the class | Refused with message to mark it Inactive instead |  | Not Run
CLS-14 | Class Sections | Permissions | Security | High | Clerk |  | As Clerk try Add / Edit / Delete class | Server refuses (403); UI shows a clear message; no data changed |  | Not Run
SUB-01 | Subjects | List | Functional | High | Admin |  | Open Subjects | List and filters (Class, Academic Year, Type) work |  | Not Run
SUB-02 | Subjects | Create | Functional | High | Admin | ZT Class A | Add 'ZT Math', class ZT Class A, Theory, max 100, pass 35 | Created |  | Not Run
SUB-03 | Subjects | Create | UI | Medium | Admin |  | Switch Type to Both | Theory max/pass and Practical max/pass fields appear; single max/pass hidden |  | Not Run
SUB-04 | Subjects | Create | Validation | Medium | Admin |  | Type Both, leave Theory max empty, Save | Message shown; nothing sent |  | Not Run
SUB-05 | Subjects | Create | Validation | High | Admin |  | Pass marks greater than max marks | Validation message |  | Not Run
SUB-06 | Subjects | Create | Functional | Low | Admin |  | Leave Code empty | Code auto-generated from the name |  | Not Run
SUB-07 | Subjects | Create | Negative | High | Admin |  | Create a second subject with the same code in the same class | Error 'Subject Code + Class must be unique' |  | Not Run
SUB-08 | Subjects | Edit | Functional | Medium | Admin |  | Edit marks and save | Saved |  | Not Run
SUB-09 | Subjects | Filters | Functional | Medium | Admin |  | Filters and search, combined | Work and combine |  | Not Run
SUB-10 | Subjects | Delete | Functional | Medium | Admin |  | Delete a subject | Confirm, then removed |  | Not Run
SUB-11 | Subjects | Teacher link | Functional | Medium | Admin | Subject assigned to a teacher | View the subject | Teacher name shown |  | Not Run
TCH-01 | Teachers | List | Functional | High | Admin |  | Open Teachers | Stat tiles (All/Active/Inactive/Suspended) show correct counts; list loads |  | Not Run
TCH-02 | Teachers | List | Functional | Medium | Admin |  | Click a status tile | List filters to that status |  | Not Run
TCH-03 | Teachers | Create | Functional | High | Admin |  | Add Teacher with all fields and a strong password (use Users & Staff > New with role Teacher if redirected) | Created; counts update; teacher can log in |  | Not Run
TCH-04 | Teachers | Create | Validation | High | Admin |  | Use weak password 'abc' | Message states exactly what is missing (8 chars, upper case, digit, special) |  | Not Run
TCH-05 | Teachers | Create | Validation | Medium | Admin |  | Leave the password empty | 'Login password is required.' |  | Not Run
TCH-06 | Teachers | Create | Negative | High | Admin |  | Use a username or e-mail that already exists | Error modal about duplicate |  | Not Run
TCH-07 | Teachers | Edit | Functional | Medium | Admin |  | Edit teacher, leave password blank, Save | Saved; old password still works |  | Not Run
TCH-08 | Teachers | Status | Security | High | Admin |  | Set the teacher to Suspended (from Users & Staff) | Counts update; teacher is signed out and can no longer log in |  | Not Run
TCH-09 | Teachers | Assignments | Functional | High | Admin | Subjects exist | Open Teacher Profile & Assignments | Stat tiles shown; assigned subjects grouped by class |  | Not Run
TCH-10 | Teachers | Assignments | Functional | High | Admin |  | Pick a class: subject checklist | Only that class's subjects; one already taught by another teacher is disabled with 'Already taught by <name>' |  | Not Run
TCH-11 | Teachers | Assignments | Functional | High | Admin |  | Assign subjects | Appear in the teacher's profile |  | Not Run
TCH-12 | Teachers | Assignments | Functional | High | Admin |  | Tick 'Assign as Class Teacher' while assigning | Class shows a star 'Class Teacher' |  | Not Run
TCH-13 | Teachers | Assignments | Negative | High | Admin | Class already has a class teacher | Make another teacher class teacher | Error naming the current class teacher |  | Not Run
TCH-14 | Teachers | Assignments | Functional | Medium | Admin |  | Unset class teacher | Star removed |  | Not Run
TCH-15 | Teachers | Assignments | Functional | Medium | Admin |  | Remove a subject assignment | Unassigned |  | Not Run
TCH-16 | Teachers | Delete | Negative | High | Admin | Teacher with assignments | Delete the teacher | Refused with counts of what blocks it |  | Not Run
TCH-17 | Teachers | Delete | Functional | Medium | Admin | Teacher without assignments | Delete the teacher | Confirm, removed; login no longer works |  | Not Run
TCH-18 | Teachers | Search | Functional | Low | Admin |  | Search by name / username / e-mail | List filters |  | Not Run
PAR-01 | Parents | List | Functional | High | Admin |  | Open Parents | List, status tiles and Contact Method filter work |  | Not Run
PAR-02 | Parents | Create | Functional | High | Admin |  | Add a parent with only name + mobile | Created |  | Not Run
PAR-03 | Parents | Create | Validation | High | Admin |  | Add without mobile; invalid e-mail | Messages shown |  | Not Run
PAR-04 | Parents | Create | Functional | Medium | Admin |  | Fill all sections (contact preferences, notification checkboxes, address) | Saved; Edit shows the same values |  | Not Run |  |  |  | Reworded Oct 15
PAR-05 | Parents | Status | Functional | Medium | Admin |  | Set status Inactive | Counts update |  | Not Run
PAR-06 | Parents | View | UI | Low | Admin |  | Click View (eye) | Details correct |  | Not Run
PAR-07 | Parents | Linked children | Functional | High | Admin | Parent with a linked student | Click Linked Children | Lists linked students with relation and primary star; empty state when none |  | Not Run
PAR-08 | Parents | Linked children | Functional | High | Admin |  | Link a student from the parent side (search student, relation, primary) | Appears in the list |  | Not Run
PAR-09 | Parents | Linked children | Negative | High | Admin |  | Link the same student again | Error 'already linked' |  | Not Run
PAR-10 | Parents | Linked children | Functional | Medium | Admin | Two parents on one student | Make the second parent primary | Star moves; only one primary |  | Not Run
PAR-11 | Parents | Linked children | Functional | Medium | Admin |  | Unlink a student | Confirm, then removed |  | Not Run
PAR-12 | Parents | Fees | UI | Low | Admin |  | Click Fee Records | 'Not yet available' style message (module not built) |  | Not Run
PAR-13 | Parents | Delete | Functional | High | Admin | Parent with NO linked children | Delete the parent | Confirm, removed (a parent with children is refused: see PAR-17) |  | Not Run |  |  |  | Reworded Oct 15
PAR-14 | Parents | Validation | Exploratory | Low | Admin | Another parent has e-mail X | Create a parent with the same e-mail X | KNOWN GAP: currently accepted. Record the result |  | Not Run
PAR-15 | Parents | Filters | Functional | Low | Admin |  | Filters and search | Work |  | Not Run
PAR-16 | Parents | Scoped access | Security | High | Teacher | Teacher is class teacher of ZT Class A | Open Parents as the teacher | Only parents of students in the teacher's own classes appear; no other family's data |  | Not Run
ADM-01 | Admissions | List / pipeline | Functional | High | Admin |  | Open Admissions | Tabs All, Registered, Admitted, Enrolled, Rejected, each with a count |  | Not Run
ADM-02 | Admissions | List / pipeline | Functional | High | Admin |  | Click each tab | Rows filter; counts match |  | Not Run
ADM-03 | Admissions | List / pipeline | Functional | Medium | Admin |  | Use filters: Academic Year, Admission Type, Applied-for Class, date from/to, search | Work and combine |  | Not Run
ADM-04 | Admissions | List / pipeline | Functional | High | Admin | One application per status | Check the row actions in each status | Registered: view, edit, confirm, reject, delete. Admitted: view, edit, enrol, reject, delete. Enrolled: view, edit, link to student, delete (no confirm/enrol/reject). Rejected: view reason, delete |  | Not Run
ADM-05 | Admissions | List / pipeline | Functional | Low | Admin |  | Export CSV | Matches the filtered rows |  | Not Run
ADM-10 | Admissions | Register | Validation | High | Admin |  | Click New Registration, Save empty | Required-field messages |  | Not Run
ADM-11 | Admissions | Register | Functional | High | Admin |  | Fill applicant, class (only Active classes listed), type, phone; Save | Saved; row under Registered with a REG-... number |  | Not Run
ADM-12 | Admissions | Register | Functional | High | Admin |  | Add a Father and a Mother row (Add guardian) | Rows with relation / name / mobile / e-mail / primary radio |  | Not Run
ADM-13 | Admissions | Register | Validation | Medium | Admin |  | Try to add a 6th guardian | Add guardian disabled at 5 |  | Not Run
ADM-14 | Admissions | Register | Validation | High | Admin |  | Add two fathers, Save | Message 'only one father and one mother' |  | Not Run
ADM-15 | Admissions | Register | Functional | Medium | Admin |  | Choose Mother as primary | Only one primary at a time |  | Not Run
ADM-16 | Admissions | Register | Functional | Low | Admin |  | Remove a guardian row | Row disappears |  | Not Run
ADM-17 | Admissions | Register | Validation | Medium | Admin |  | Enter a date of birth in the future | Error |  | Not Run
ADM-18 | Admissions | Register | Functional | Medium | Admin |  | Register with no guardians | Allowed |  | Not Run
ADM-19 | Admissions | Register | Functional | Medium | Admin |  | In Documents choose the Document type FIRST, then add a file; Save | The file picker stays disabled until a type is chosen; each file gets that type (changeable per file); application saved together with the document(s) |  | Not Run |  |  |  | Reworded Oct 16
ADM-20 | Admissions | Edit | Functional | High | Admin | Registered application | Edit phone and replace guardians; Save; reopen | New values shown |  | Not Run
ADM-21 | Admissions | Confirm | Functional | High | Admin | Registered application | Confirm Admission: fee 500, payment reference, blood group, religion, category, notes | Fee amount and Payment reference both show a red star; moves to Admitted; fee visible in details |  | Not Run |  |  |  | Reworded Oct 16
ADM-22 | Admissions | Confirm | Validation | Medium | Admin |  | Negative fee | Error |  | Not Run
ADM-23 | Admissions | Confirm | UI | Low | Admin |  | Religion and Category fields | Fixed lists, no free text |  | Not Run
ADM-24 | Admissions | Reject | Functional | High | Admin |  | Reject an application | Modal asks for a reason; empty reason blocked; saved reason shown via View Rejection Reason |  | Not Run
ADM-25 | Admissions | Reject | Negative | Medium | Admin | Enrolled application | Look for Reject | Action not offered |  | Not Run
ADM-26 | Admissions | Delete | Functional | Medium | Admin |  | Delete an application | Confirm, disappears |  | Not Run
ADM-G01 | Admissions | Existing parent (G2) | Functional | High | Admin | Parent 'ZT Father' exists with a linked child | In New Registration add a guardian and use 'Pick an existing parent'; type 2+ letters of the name | Results show name, mobile and the child names already linked to that parent |  | Not Run
ADM-G02 | Admissions | Existing parent (G2) | Functional | High | Admin |  | Search by mobile number (3+ digits) | Matching parent(s) listed; maximum 10 results |  | Not Run
ADM-G03 | Admissions | Existing parent (G2) | Validation | Low | Admin |  | Type only 1 character | No search runs / hint to type more |  | Not Run
ADM-G04 | Admissions | Existing parent (G2) | Functional | High | Admin |  | Select a parent; look at the guardian row; Save | Guardian row shows the parent's name, mobile and e-mail (read-only); saved; reopening shows the same link |  | Not Run
ADM-G05 | Admissions | Existing parent (G2) | Functional | High | Admin | Guardian linked to a parent | Change the typed name/mobile in the form, if the fields are editable, and Save | The saved guardian still has the PARENT's name/mobile/e-mail (server copies from the parent record) |  | Not Run
ADM-G06 | Admissions | Existing parent (G2) | Functional | Medium | Admin | Linked guardian | Choose 'Use a different person' and type the details by hand | Link removed; typed details saved |  | Not Run
ADM-G07 | Admissions | Existing parent (G2) | Negative | High | Admin |  | Pick the same parent for both Father and Mother | Refused with a clear message (a parent cannot be two guardians); nothing saved |  | Not Run
ADM-G08 | Admissions | Existing parent (G2) | Functional | Medium | Admin | Mobile typed by hand matches an existing parent | Type a mobile that belongs to an existing parent in a guardian row | A hint offers the matching parent (shown only to users with Parents.View) |  | Not Run
ADM-G09 | Admissions | Existing parent (G2) | Security | High | Clerk without Parents.View | Role without Parents.View but with Admissions.Create | Open New Registration | No parent search, no mobile hint and no children are shown; typing guardians by hand still works |  | Not Run
ADM-G10 | Admissions | Existing parent (G2) | Security | High | Clerk without Parents.View | Application already linked to a parent by an Admin | Edit the application remarks and Save | Saved without error; link kept |  | Not Run
ADM-G11 | Admissions | Existing parent (G2) | Security | High | Role without Admissions.Create/Edit | Role has Parents.View only | Call the search (or open the screen) | Refused (403); no parent data returned |  | Not Run
ADM-G12 | Admissions | Existing parent (G2) | Functional | High | Admin | Admitted application whose Father is linked to ZT Father | Click Enroll to Class | Guardian pre-selected as 'Use existing: ZT Father' even if the typed mobile differs |  | Not Run
ADM-G13 | Admissions | Existing parent (G2) | Functional | High | Admin |  | Enrol with the pre-selected parent | Student created and linked to that parent; no duplicate parent created (check Parents list) |  | Not Run
ADM-G14 | Admissions | Existing parent (G2) | Functional | High | Admin | Same as ADM-G12 | In the enrol dialog choose a DIFFERENT parent (or Create new) and enrol | Enrolment succeeds with the chosen parent; ask a developer / check audit log: the change is recorded with old parent, new parent, user and time |  | Not Run
ADM-G15 | Admissions | Existing parent (G2) | Negative | High | Admin | Linked parent was deleted after registration | Click Enroll to Class | Enrol is refused with a clear message to open the application and choose 'Use a different person'; no student and no new parent created |  | Not Run
ADM-G16 | Admissions | Existing parent (G2) | Functional | Medium | Admin | Two guardians linked to two different parents | In enrol, swap the two parents between the guardians | Succeeds; each guardian ends up with the chosen parent |  | Not Run
ADM-G17 | Admissions | Existing parent (G2) | Functional | Medium | Admin | Guardian mobile equals a parent linked to ANOTHER guardian | Open enrol | That guardian is not pre-selected; staff must choose |  | Not Run
ADM-30 | Admissions | Enrol | Functional | High | Admin | Admitted application, Father+Mother whose mobiles match existing parents | Click Enroll to Class | Modal loads guardian matches; each pre-selected 'Use existing: <parent>' |  | Not Run
ADM-31 | Admissions | Enrol | Functional | High | Admin |  | Guardian mobile matches nobody | Pre-selected 'Create new parent' |  | Not Run
ADM-32 | Admissions | Enrol | Functional | High | Admin | Two parents share the mobile | Open enrol | No pre-selection; staff must choose (or search another parent) |  | Not Run
ADM-33 | Admissions | Enrol | Validation | High | Admin | Guardian without mobile | Open enrol | Enrol button blocked with a message |  | Not Run
ADM-34 | Admissions | Enrol | Validation | High | Admin |  | Choose the same existing parent for two guardians | Blocked with message |  | Not Run
ADM-35 | Admissions | Enrol | Functional | Medium | Admin |  | Use 'Search another parent...' and select one | Search lists all parents; selecting sets the decision |  | Not Run
ADM-36 | Admissions | Enrol | Functional | High | Admin |  | Leave roll number and admission number BLANK; set date and class (Active classes only) | Accepted; the student gets a roll number like 5A001 and an admission number like ADM-2026-0001 |  | Not Run |  |  |  | Reworded Oct 16
ADM-37 | Admissions | Enrol | Negative | High | Admin | Roll number typed by hand that is already used in that class | Type that roll number and submit | Error 'already taken' |  | Not Run |  |  |  | Reworded Oct 16
ADM-38 | Admissions | Enrol | Negative | High | Admin | Class at capacity | Submit | Error 'is full (n/n)' |  | Not Run
ADM-39 | Admissions | Enrol | Functional | High | Admin |  | Submit a valid enrolment | Application becomes Enrolled; student appears in Students; new parents appear if Create new was chosen |  | Not Run
ADM-40 | Admissions | Enrol | Negative | High | Admin |  | Stop the API / cut network, then submit | Error shown; NO partial student or parent created |  | Not Run
ADM-41 | Admissions | Enrol | Negative | Medium | Admin |  | Double-click the Enrol button | Only one student created |  | Not Run
STU-01 | Students | List | Functional | High | Admin |  | Open Students | Tabs All, Active, Inactive, Left with counts |  | Not Run
STU-02 | Students | List | Functional | Medium | Admin |  | Filters: Class, Gender, Curriculum, House, has allergies | Work and combine; allergy filter uses health data (no English-level filter any more) |  | Not Run |  |  |  | Reworded Oct 15
STU-03 | Students | List | Functional | Medium | Admin |  | Search (header + quick search) | Filters by name / admission number |  | Not Run
STU-04 | Students | List | UI | Low | Admin |  | Hover the row actions | View, Fee Summary, Attendance Report, Report Card, Linked Parents, Academic History, Edit, Mark as left (no Delete) |  | Not Run |  |  |  | Reworded Oct 15
STU-05 | Students | List | UI | Low | Admin |  | Click Fee Summary / Attendance Report / Report Card | 'Not yet available' modal naming the missing module |  | Not Run
STU-06 | Students | List | Functional | Medium | Admin |  | Export CSV | Correct columns |  | Not Run
STU-07 | Students | List | Functional | Medium | Admin | A Left student | Check tabs | Left students shown under All and Left only, with a purple badge |  | Not Run
STU-10 | Students | View | Functional | High | Admin | Student enrolled via admission | Open View | Sections Basics, Academic, Health, Parents etc. filled; blood group from health |  | Not Run
STU-11 | Students | Edit | Functional | High | Admin |  | Open Edit | All sections load (health, pickup persons, identity) |  | Not Run
STU-12 | Students | Edit | Functional | High | Admin |  | Change personal data and Save | Reflected in list and view |  | Not Run
STU-13 | Students | Edit | UI | Medium | Admin |  | Look at the Parents/Guardians section in the modal | Read-only, with hint to manage links from Parents |  | Not Run
STU-14 | Students | Edit | Functional | Medium | Admin |  | Add two pickup persons (name, relation, phone, ID note) | Saved; shown on reopen |  | Not Run
STU-15 | Students | Edit | Validation | Medium | Admin |  | Invalid phone on a pickup person | Validation message |  | Not Run
STU-16 | Students | Edit | Functional | Low | Admin |  | Remove all pickup persons and save | Gone on reopen |  | Not Run
STU-17 | Students | Edit | Functional | Medium | Admin |  | Fill health (blood group, allergies, notes) | Saved; allergy chip/filter works |  | Not Run
STU-18 | Students | Identity | Security | High | Admin |  | Open Identity Documents as Admin | Editable; full values on reopen |  | Not Run
STU-19 | Students | Identity | Security | High | Clerk |  | Open the same student as Clerk | Values masked (e.g. ********9012); fields NOT editable |  | Not Run
STU-20 | Students | Identity | Validation | Medium | Admin |  | Aadhaar not 12 digits | Message |  | Not Run
STU-21 | Students | Identity | Negative | Medium | Admin | Aadhaar used by another student | Save the same Aadhaar on a second student | Error 'already recorded for another student' |  | Not Run
STU-22 | Students | Create (via enrolment) | Functional | High | Admin | An application in status Admitted; a class with free seats | Open the application, choose Enrol; leave roll and admission number blank; choose class and date; add the guardians; confirm | Student created as Active; roll number (class + section + 3 digits) and admission number (ADM-year-serial) generated; application becomes Enrolled; History tab shows one Active period; parents linked |  | Not Run |  |  |  | Reworded: there is no Add Student screen; students are created only by enrolling an admission.; Reworded Oct 16
STU-23 | Students | Create (via enrolment) | Negative | High | Admin | An existing student; a second Admitted application | Enrol the application using (a) the existing admission number, then (b) a new admission number but a roll number already used in the same class | (a) Error: admission number is already used by another student. (b) Error: roll number is already taken in that class. No student is created and the application stays Admitted. |  | Not Run |  |  |  | Reworded: duplicate checks are tested through Enrol.
STU-24 | Students | Edit | UI | Low | Admin |  | Open the status options | Only Active / Inactive / Left |  | Not Run
STU-25 | Students | Class move | Functional | High | Admin | Two classes, same academic year | Change class in Edit, Save | List shows new class; History shows Transferred + Active rows |  | Not Run
STU-26 | Students | Class move | Negative | High | Admin |  | Move to an inactive or full class | Error modal |  | Not Run
STU-27 | Students | Class move | Negative | Medium | Admin | Class of another academic year | Pick it and save | Error about year-end promotion |  | Not Run
STU-28 | Students | Status | Negative | High | Admin |  | Set Left and change class in the same edit | Error 'cannot be moved ... and marked as Left in the same edit' |  | Not Run
STU-29 | Students | Status | Functional | High | Admin |  | Set status Left | Row moves to Left; History shows a closing 'Left' row |  | Not Run
STU-30 | Students | Status | Functional | Medium | Admin | A Left student | Set back to Active | New Active row in History |  | Not Run
STU-31 | Students | Left | Functional | Medium | Admin |  | Look for a Delete button on the Students list and on a student's page | There is none: a student who has gone is closed with Mark as left (see STU-49) |  | Not Run |  |  |  | Reworded Oct 15
STU-40 | Students | History | Functional | High | Admin |  | Open Academic History for a normal student | One row: year, class, roll, from date, dash, Active badge |  | Not Run
STU-41 | Students | History | Functional | High | Admin | After a class change | Open Academic History | Two rows, newest first; old row has end date, Transferred and remark 'Moved to ...' |  | Not Run
STU-42 | Students | History | UI | Low | Admin |  | Look for edit controls in the history | Read-only |  | Not Run
STU-43 | Students | History | Negative | Low | Admin |  | Open history with API stopped | 'Loading...' then 'Could not load the history.' |  | Not Run
STU-44 | Students | Linked parents | Functional | Medium | Admin |  | Open Linked Parents | Parents with relation, primary star, mobile/e-mail; empty state when none |  | Not Run
STU-45 | Students | Student detail | Functional | Medium | Admin |  | Open a student's detail page | Tabs (basics, history, health, documents, ...) load; Safeguarding/Documents only for office staff with the permission |  | Not Run
STU-46 | Students | Scoped access | Security | High | Teacher | Teacher is class teacher of ZT Class A | Open Students as the teacher | Only students of the teacher's classes are listed; others cannot be opened by URL |  | Not Run
ATT-01 | Attendance | Open | Functional | High | Admin |  | Open Attendance | Tabs Daily / Subject; Class, Date (today) and Search present |  | Not Run
ATT-02 | Attendance | Roster | Functional | High | Admin | Class with students | Pick a class | Roster of Active students: roll no., name, admission no., 5 status buttons, remarks, last-7 dots |  | Not Run
ATT-03 | Attendance | Subject tab | Functional | Low | Admin | Class with no subjects | Open Subject tab | Message 'No active subjects' |  | Not Run
ATT-04 | Attendance | Subject tab | Functional | Medium | Admin |  | Subject tab without choosing a subject | Roster not loaded / prompt to choose |  | Not Run
ATT-05 | Attendance | Marking | Functional | High | Admin |  | Mark All Present | Everyone Present; counters update |  | Not Run
ATT-06 | Attendance | Marking | Functional | Medium | Admin |  | Mark All Absent | Everyone Absent |  | Not Run
ATT-07 | Attendance | Marking | Functional | High | Admin |  | Change individual statuses and add remarks | Counters (Present/Absent/Late/Half Day/Leave) update live |  | Not Run
ATT-08 | Attendance | Save | Validation | High | Admin |  | Save with a student unmarked | Error 'N student(s) have no status yet' (or Save disabled until complete; record which) |  | Not Run
ATT-09 | Attendance | Save | Functional | High | Admin |  | Save | Banner 'Saved by <user> - <time>'; Save disabled until something changes |  | Not Run
ATT-10 | Attendance | Save | Functional | High | Admin | Saved earlier | Reload and re-select class and date | Saved statuses come back |  | Not Run
ATT-11 | Attendance | Save | Functional | Medium | Admin |  | Change a status and save again | Same session updated; banner time changes |  | Not Run
ATT-12 | Attendance | Copy | Functional | Medium | Admin | Previous day saved | Click Copy from previous day | Statuses copied from the previous session date; button disabled when none exists |  | Not Run
ATT-13 | Attendance | Search | Functional | Medium | Admin |  | Search students by name / admission / roll | Visible rows filter; hidden rows keep their status and are still saved |  | Not Run
ATT-14 | Attendance | Unsaved changes | Functional | High | Admin | Unsaved changes | Change class / date / tab | Confirm 'Discard unsaved changes?' |  | Not Run
ATT-15 | Attendance | Unsaved changes | Functional | Medium | Admin | Unsaved changes | Close or refresh the browser tab | Browser 'leave site?' warning |  | Not Run
ATT-16 | Attendance | Rules | Negative | High | Admin |  | Select a future date | Banner 'cannot be marked for a future date'; buttons disabled |  | Not Run
ATT-17 | Attendance | Rules | Security | High | Clerk | Date 2 or more days ago (older than yesterday) | Open that date as Clerk or Teacher, then as Admin | Non-admin: locked ('Only an Admin can change attendance older than 1 day'); Admin can edit |  | Not Run |  |  |  | Reworded Oct 15
ATT-18 | Attendance | Teacher | Functional | High | Teacher | zt.teacher1 is class teacher of Class A | Log in as the teacher, class A, Daily | Editable |  | Not Run
ATT-19 | Attendance | Teacher | Security | High | Teacher |  | Teacher opens a class they are NOT class teacher of | Locked banner; read-only |  | Not Run
ATT-20 | Attendance | Teacher | Security | Medium | Teacher |  | Teacher opens Subject tab for a subject they do not teach | Locked banner |  | Not Run
ATT-21 | Attendance | History | Functional | Medium | Admin | Student moved out of class after the date | View the old date and a new date | Student still shown for the old date; absent for new dates |  | Not Run
ATT-22 | Attendance | History | Functional | Low | Admin | Left student recorded earlier | View an old date | Marked as not active in class (greyed) on old dates |  | Not Run
ATT-23 | Attendance | Sessions | Functional | Medium | Admin |  | Mark Daily and Subject attendance for the same day | Independent sessions |  | Not Run
ATT-24 | Attendance | Performance | UI | Low | Admin | Class of 40+ students | Mark and save | Scrolls smoothly; save under 2 seconds |  | Not Run
ATT-25 | Attendance | Date rule | Exploratory | Medium | Admin | Test between 00:00 and 04:00 Abu Dhabi time | Open Attendance and look at 'today' | KNOWN LIMITATION in this build: 'today' follows UTC, so it can still show yesterday during those hours (fixed in the next change F2). Record what you see |  | Not Run
DOC-01 | Documents | Documents page | Functional | High | Admin | Documents exist | Open Documents | List loads; filters work (type, status, expiry state Expired / Expiring soon, owner) |  | Not Run
DOC-02 | Documents | Upload | Functional | High | Admin | A student exists | On the student's Documents tab upload a PDF of type 'Transfer certificate' | Uploaded; status Pending; shows file name, size, type, uploader |  | Not Run
DOC-03 | Documents | Upload | Functional | High | Admin |  | Upload a JPG and a PNG | Both accepted |  | Not Run
DOC-04 | Documents | Upload | Negative | High | Admin | A small .exe or .txt file renamed to .pdf | Upload it | Refused: the file CONTENT is checked, not the name |  | Not Run
DOC-05 | Documents | Upload | Functional | Low | Admin | A real PNG named scan.pdf | Upload it | Accepted as a PNG; downloads as scan.png |  | Not Run
DOC-06 | Documents | Upload | Negative | High | Admin | A file over 5 MB | Upload it | Refused with a message showing the file size and the limit |  | Not Run
DOC-07 | Documents | Upload | Validation | High | Admin |  | Upload type Passport / Residence visa / Emirates ID without an expiry date | Expiry date required message |  | Not Run
DOC-08 | Documents | Upload | Validation | Medium | Admin |  | Upload type Birth certificate (no expiry) | No expiry field required |  | Not Run
DOC-09 | Documents | Upload | Negative | High | Admin |  | Upload the exact same file to the same student again | Refused (duplicate) |  | Not Run
DOC-10 | Documents | Upload | Functional | Medium | Admin |  | Upload several files at once | Per-file result shown (success / reason for each) |  | Not Run
DOC-11 | Documents | Review | Functional | High | Admin (reviewer) | Document uploaded by ANOTHER user | Verify the document | Status Verified; reviewer and time shown |  | Not Run
DOC-12 | Documents | Review | Functional | High | Admin (reviewer) |  | Reject a document | Reason required; status Rejected; reason visible |  | Not Run
DOC-13 | Documents | Review | Negative | High | Admin | Document uploaded by yourself | Try to verify or reject your own upload | Refused (nobody reviews their own upload) |  | Not Run
DOC-14 | Documents | Review | Functional | Medium | Admin (reviewer) | Verified document | Unverify | Back to Pending |  | Not Run
DOC-15 | Documents | Review | Negative | Medium | Admin (reviewer) | Rejected document | Look for a way to reopen it | Not reopened; upload a new document instead |  | Not Run
DOC-16 | Documents | Delete | Negative | High | Admin | Verified document | Delete it | Refused: 'Unverify it first' |  | Not Run
DOC-17 | Documents | Delete | Functional | Medium | Admin | Pending document | Delete it | Confirm, removed from the list |  | Not Run
DOC-18 | Documents | Download | Functional | High | Admin |  | Download a document | File opens correctly and matches what was uploaded |  | Not Run
DOC-19 | Documents | Download | Security | High | User with Documents.View but not Students.ViewSensitive | Document of a sensitive type (Passport, Emirates ID, Aadhaar, Medical record, ...) | Try to download | Refused (403) |  | Not Run
DOC-20 | Documents | Expiry | Functional | Medium | Admin | Documents with expiry dates in the past / next 30 days | Filter Expired and Expiring soon | Correct documents listed in each filter |  | Not Run
DOC-21 | Documents | Permissions | Security | High | Clerk / Teacher | Role without Documents permissions | Open Documents or a student's Documents tab | No documents shown / no access; API refuses (403) |  | Not Run
DOC-22 | Documents | Applications | Functional | Medium | Admin | Application with documents | Enrol the application | Record what happens to the documents (expected: visible on the new student record) |  | Not Run
DOC-23 | Documents | Applications | Negative | Medium | Admin | Enrolled application | Try to upload a document to the application | Refused (it is already a student) |  | Not Run
USR-01 | Users & Staff | List | Functional | High | Admin |  | Open Users & Staff | List loads with name, username, role, status, last login; filters/search work |  | Not Run
USR-02 | Users & Staff | Create | Functional | High | Admin |  | New user: username, e-mail, role (e.g. Clerk), full name, gender, mobile, joining date, temporary password | Created; appears in list; status Active |  | Not Run
USR-03 | Users & Staff | Create | Functional | High | Admin |  | Log in as the new user with the temporary password | Forced to change password before anything else |  | Not Run
USR-04 | Users & Staff | Create | Validation | High | Admin |  | Leave required fields empty / weak password / bad e-mail | Clear messages; nothing created |  | Not Run
USR-05 | Users & Staff | Create | Negative | High | Admin |  | Reuse an existing username or e-mail | Error modal about duplicate |  | Not Run
USR-06 | Users & Staff | Create | Negative | Medium | Admin |  | Try to create a user with role Student or Parent | Not offered / refused (portal logins are not built yet) |  | Not Run
USR-07 | Users & Staff | Create | Functional | High | Admin |  | Create a user with role Teacher | Teacher also appears in the Teachers page and can be given assignments at once |  | Not Run
USR-08 | Users & Staff | Edit | Functional | High | Admin |  | Edit another user's username, e-mail, profile fields | Saved and shown on the detail page |  | Not Run
USR-09 | Users & Staff | Edit | Functional | High | Admin | Logged-in target user | Change a user's role; that user's next request | New role's permissions apply on their next request (menus and access change) |  | Not Run
USR-10 | Users & Staff | Edit | Negative | High | Admin |  | Change YOUR OWN role, status, or delete yourself | Refused ('use My Account') |  | Not Run
USR-11 | Users & Staff | Edit | Negative | Medium | Admin | Teacher with subject assignments | Change that user's role away from Teacher | Refused while assignments exist |  | Not Run
USR-12 | Users & Staff | Status | Security | High | Admin | Target user logged in elsewhere | Set status to Inactive, then Suspended | Target is signed out; cannot log in until Active again |  | Not Run
USR-13 | Users & Staff | Status | Negative | High | Admin | Only one active Admin | Try to deactivate, suspend, demote or delete the last active Admin | Refused with a clear message |  | Not Run
USR-14 | Users & Staff | Reset password | Functional | High | Admin |  | Reset a user's password | Temporary password shown ONCE on screen; user must change it at next login; their sessions end |  | Not Run
USR-15 | Users & Staff | Unlock | Functional | High | Admin | Locked account (see LOG-13) | Click Unlock | User can log in again |  | Not Run
USR-16 | Users & Staff | Delete | Functional | High | Admin |  | Delete a user | Confirm; removed from list; cannot log in; username/e-mail can be reused |  | Not Run
USR-17 | Users & Staff | Delete | Negative | Medium | Admin | Teacher with assignments | Delete that user | Refused with counts |  | Not Run
USR-18 | Users & Staff | Roles | Security | High | Admin / lower role | User whose role lacks some permissions | Try to give a user a role that holds permissions you do not hold | Refused |  | Not Run
USR-19 | Users & Staff | Detail | UI | Low | Admin |  | Open a user's detail page | All sections shown; empty values as dashes |  | Not Run
USR-20 | Users & Staff | Addresses | Functional | Medium | Admin |  | Add / edit / remove addresses in the staff form | Saved; primary address rule respected (one primary) |  | Not Run
USR-21 | Users & Staff | Permissions | Security | High | Clerk | Role without Users permissions | Open Users & Staff or call the page by URL | No access / clear message; no user data shown |  | Not Run
USR-22 | Users & Staff | Concurrency | Negative | Low | Admin | Two Admins editing the same user | Both open the user; one saves; the other then saves | Second save refused with a 'changed by someone else' message; no silent overwrite |  | Not Run
ROL-01 | Roles & Permissions | List | Functional | High | Admin |  | Open Roles & Permissions | Roles list with status and user counts |  | Not Run
ROL-02 | Roles & Permissions | Create | Functional | High | Admin |  | Create a role with a name and a set of permissions using the permission picker | Created; summary shows the chosen permissions |  | Not Run
ROL-03 | Roles & Permissions | Picker | UI | Medium | Admin |  | Tick a whole module / group in the picker | Tri-state checkbox: all / some / none shown correctly |  | Not Run
ROL-04 | Roles & Permissions | Picker | Functional | High | Admin |  | Tick an 'Edit' permission without 'View' | Dependent permissions are added or the user is told (record behaviour) |  | Not Run
ROL-05 | Roles & Permissions | Create | Negative | Medium | Admin |  | Duplicate role name | Error |  | Not Run
ROL-06 | Roles & Permissions | Edit | Functional | High | Admin | Role assigned to a user | Remove a permission from the role | Affected users lose it (record whether they must log in again or only refresh) |  | Not Run
ROL-07 | Roles & Permissions | Status | Functional | Medium | Admin |  | Deactivate then activate a role | Confirmation dialog; status changes; users with a deactivated role are handled as designed (record behaviour) |  | Not Run
ROL-08 | Roles & Permissions | Delete | Negative | Medium | Admin | Role assigned to users | Delete the role | Refused while users hold it |  | Not Run
ROL-09 | Roles & Permissions | Built-in roles | Exploratory | Medium | Admin |  | Try to edit / delete the built-in roles (Admin, Supervisor, Clerk, Teacher) | Record what is allowed; Admin must never lose the ability to manage the system |  | Not Run
ROL-10 | Roles & Permissions | Security | Security | High | Role holder | User who lacks some permission P | Edit a role to include P | Refused (you cannot grant permissions you do not hold) |  | Not Run
ROL-11 | Roles & Permissions | Permissions | Security | High | Clerk | Role without Roles permissions | Open Roles & Permissions | No access / clear message |  | Not Run
ACC-01 | My Account | Profile | Functional | High | Any staff | Logged in | Open My Account | Own profile, e-mail, addresses, password section shown |  | Not Run
ACC-02 | My Account | Profile | Functional | High | Any staff |  | Edit full name, mobile, date of birth, qualification, emergency contact, blood group; Save | Saved; shown again after reload |  | Not Run
ACC-03 | My Account | Profile | Security | High | Any staff |  | Look for username, role, status, joining date | Not editable by the user |  | Not Run
ACC-04 | My Account | Profile | Validation | Medium | Any staff |  | Invalid mobile / e-mail; e-mail used by someone else | Clear messages |  | Not Run
ACC-05 | My Account | Addresses | Functional | Medium | Any staff |  | Add / edit address | Saved |  | Not Run
ACC-06 | My Account | Password | Functional | High | Any staff |  | Change password with the correct current password and a strong new one | Success; other sessions end; new password works |  | Not Run
ACC-07 | My Account | Password | Negative | High | Any staff |  | Wrong current password / weak new password / new = old | Clear messages; password unchanged |  | Not Run
ACC-08 | My Account | Theme | UI | Low | Any staff |  | Change theme | Saved per user and kept after logout/login |  | Not Run
ACC-09 | My Account | Forced change | Functional | High | New user | MustChangePassword set | Log in and try to open another page | Only the Change Password page is reachable until done |  | Not Run
SET-01 | School Settings | View | Functional | High | Admin |  | Open Settings | Identity, Contact, Time zone & currency, Working days, About sections load with current values |  | Not Run
SET-02 | School Settings | Edit | Functional | High | Admin |  | Change school name and Save | Saved; top bar shows the new name after refresh |  | Not Run
SET-03 | School Settings | Edit | Validation | High | Admin |  | Clear the school name; invalid e-mail / website / phone | Clear messages; nothing saved |  | Not Run
SET-04 | School Settings | Edit | Validation | High | Admin |  | Currency code not 3 capital letters; invalid time zone | Refused with message |  | Not Run
SET-05 | School Settings | Edit | Validation | High | Admin |  | Untick all working days, Save | Refused: at least one working day required |  | Not Run
SET-06 | School Settings | Edit | Functional | Medium | Admin |  | Change country, time zone, currency, working days; Save; reload | Values persist |  | Not Run
SET-07 | School Settings | Concurrency | Negative | Medium | Admin | Two Admins on Settings | Both open; one saves; the other saves | Second save refused with a conflict message |  | Not Run
SET-08 | School Settings | Permissions | Security | High | Clerk / Teacher | Role without Settings permissions | Open Settings | No access / clear message |  | Not Run
SET-09 | School Settings | Permissions | Security | Medium | User with Settings.View only |  | Open Settings | Fields visible but not editable / Save refused |  | Not Run
DSH-01 | Dashboard | Dashboard | Functional | Low | Admin |  | Open the Dashboard | Welcome message shown (no widgets built yet); no errors |  | Not Run
RBAC-01 | Roles & Access (RBAC) | Clerk | Security | High | Clerk |  | Try to add a class / student / parent / teacher | 403 shown as a clear 'You do not have permission' message; no crash; no data created |  | Not Run
RBAC-02 | Roles & Access (RBAC) | Clerk | Security | High | Clerk | Student with identity numbers | View the student | Identity numbers masked |  | Not Run
RBAC-03 | Roles & Access (RBAC) | Supervisor | Security | Medium | Supervisor |  | View a student's identity numbers; try to edit them | Supervisor can view as the role allows, but cannot edit identity: that needs both Students.Edit and Students.ViewSensitive (expect the edit to be hidden or refused with 403) |  | Not Run |  |  |  | Reworded Oct 15
RBAC-04 | Roles & Access (RBAC) | Teacher | Functional | High | Teacher |  | Mark attendance for own class | Works |  | Not Run
RBAC-05 | Roles & Access (RBAC) | Teacher | Security | High | Teacher |  | Look for Admissions in the menu; type /admissions in the address bar | Admissions is not in the Teacher menu; the URL redirects away (Teacher has no Admissions.View); nothing created |  | Not Run |  |  |  | Reworded Oct 15
RBAC-06 | Roles & Access (RBAC) | Permission change | Functional | High | Admin | User logged in | Admin changes the user's role/permissions | User gets the new rights on next request (record whether re-login is needed) |  | Not Run
RBAC-07 | Roles & Access (RBAC) | Direct URL | Security | High | Any | User without permission for a page | Type that page's URL | No data shown; safe redirect or message |  | Not Run
RBAC-08 | Roles & Access (RBAC) | API | Security | High | Any |  | (Technical tester) call an endpoint with a missing / expired / another user's token in Swagger or Postman | 401 for no/invalid token, 403 for missing permission, never data |  | Not Run
E2E-01 | End-to-End | Full school day | Functional | High | Admin | Clean ZT test data | 1) Admin logs in. 2) Create 'ZT Class A' (cap 30) and 'ZT Class B'. 3) Subject 'ZT Math' in A. 4) Create teacher zt.teacher1, assign Math in A and make class teacher. 5) Parent 'ZT Father' mobile 9876501111. 6) Register 'ZTKid One' with Father (same mobile) and Mother (new mobile); confirm with fee 500; enrol into A. | Father matched to the existing parent, Mother created new; student Active; Linked Parents shows both; History shows one Active row |  | Not Run
E2E-02 | End-to-End | Full school day | Functional | High | Admin | After E2E-01 | Edit the student: allergy, one pickup person, blood group; reopen. Move to Class B, then back to A | Everything persisted; History shows Transferred + Active and then a third row |  | Not Run
E2E-03 | End-to-End | Full school day | Functional | High | Admin | After E2E-02 | Mark class A today: Mark All Present, one Late, one Absent; Save; reload | Saved values returned |  | Not Run
E2E-04 | End-to-End | Full school day | Security | High | Teacher / Clerk | After E2E-03 | Log in as zt.teacher1: class A editable, class B read-only. Log in as Clerk: identity masked, adding a class gives a friendly 403 | As stated |  | Not Run
E2E-05 | End-to-End | Full school day | Functional | Medium | Admin |  | Reject a new application with a reason; open View Rejection Reason. Then delete all ZT data in reverse order | Reason shown; deletions succeed in order (students, parents, subjects, teachers, classes) |  | Not Run
E2E-06 | End-to-End | Sibling admission | Functional | High | Admin |  | Register two applicants with the SAME father mobile; enrol the first with Father 'Create new'. Register the second and pick the same father with 'Pick an existing parent'; enrol it | Second child linked to the same father; Parents list shows one father with two children; no duplicate parent |  | Not Run
E2E-07 | End-to-End | Sibling admission | Functional | Medium | Admin |  | Create a second parent with the same mobile; enrol a third applicant typed with that mobile | Enrol dialog forces a choice and shows both candidates |  | Not Run
E2E-08 | End-to-End | Class full / inactive | Functional | Medium | Admin |  | Class capacity 1: enrol one student, try a second. Then deactivate a class | Second enrolment 'is full'; inactive class disappears from application/enrol class lists; existing applicant can still be edited |  | Not Run
E2E-09 | End-to-End | Left and return | Functional | Medium | Admin |  | Mark a student Left; check class strength and attendance roster for a new date; set Active again | Strength drops then returns; roster excludes the student while Left; History has Left then new Active row |  | Not Run
E2E-10 | End-to-End | Staff lifecycle | Functional | High | Admin |  | Create a Clerk user -> log in (forced password change) -> Admin resets password -> suspend -> unlock/activate -> delete | Each step behaves as the USR cases; deleted user cannot log in and username is reusable |  | Not Run
E2E-11 | End-to-End | Documents | Functional | High | Admin | Two Admin-level users (one uploads, one reviews) | Register an application with a Birth certificate; confirm; enrol; reviewer verifies the document; check it on the student; unverify; delete | Document is visible on the student (record if not); no self-review; a verified document cannot be deleted until unverified |  | Not Run
NFR-01 | Non-functional | Browsers | UI | Medium | Any |  | Repeat a core flow (login, admission, attendance) on Chrome and Edge (and Firefox/Safari if used) | Same behaviour |  | Not Run
NFR-02 | Non-functional | Accessibility | UI | Medium | Any |  | Use only the keyboard on a form: Tab order, Enter to submit, Esc to close modals | Logical order, visible focus |  | Not Run
NFR-03 | Non-functional | Zoom | UI | Low | Any |  | Browser zoom 150% | Layout intact |  | Not Run
NFR-04 | Non-functional | Volume | Functional | Low | Admin | ~500 students (seed via SQL) | Open Students, filter, search | Page renders in about 2 s; filters stay responsive |  | Not Run
NFR-05 | Non-functional | Slow network | Negative | Low | Any |  | Use browser 'Slow 3G'; save something | Loading states visible; no duplicate submissions |  | Not Run
NFR-06 | Non-functional | Double submit | Negative | Medium | Any |  | Double-click Save buttons on each form | One request / one record each |  | Not Run
NFR-07 | Non-functional | Console / network | Functional | High | Any | DevTools open | Run through any module | No red console errors; no 500 responses at any point |  | Not Run
NFR-08 | Non-functional | Dates | Exploratory | Low | Any |  | Check date display and entry (dd/mm/yyyy vs mm/dd) on several forms | Consistent and unambiguous; invalid dates refused |  | Not Run
LOG-16 | Login & Layout | Login page | UI | Medium | None | Logged out | Open the login page | Heading 'Sign in to Escoule'; brand name Escoule on the left; under the Sign in button: 'Forgot your password? Ask your administrator to reset it.' |  | Not Run |  |  |  | New Oct 15
LAY-09 | Login & Layout | Branding | UI | Medium | Admin | Logged in | Look at the sidebar header, the footer and the browser tab title | Shows 'Escoule' only: no 'Synergein School' and no 'Demo School' |  | Not Run |  |  |  | New Oct 15
CMP-11 | Reusable Components | Searchable dropdown | Functional | Medium | Admin | A dropdown with 6 or more options (Nationality, Class on Attendance, a list filter) | Open it, type part of an option, use Arrow keys and Enter; press Esc | A search box sits at the top; the list narrows as you type; Enter picks the highlighted option; Esc closes without changing; 'No matches' when nothing fits; dropdowns with fewer than 6 options stay a plain list |  | Not Run |  |  |  | New Oct 15
CMP-12 | Reusable Components | Fixed tabs | UI | Medium | Admin | None | Open an Add/Edit full-page form (e.g. Edit Student); click each section tab; clear a required field and Save | Only the clicked section shows and its tab is highlighted; no sideways scrolling; after a failed save the first tab with an error opens and shows a red count |  | Not Run |  |  |  | New Oct 15
ADM-42 | Admissions | List | UI | Low | Admin | None | Open Admissions and an application's page | Column and header read 'Reg No' (not 'REG #') |  | Not Run |  |  |  | New Oct 15
ADM-43 | Admissions | Register - class choice | Functional | High | Admin | Classes 'Class 1 A' and 'Class 1 B' exist | New Registration > open the Class list | One entry per class with its academic year (e.g. 'Class 1 (2026-2027)'), no section; hint says the section is chosen at enrolment; list and details show the class without a section after saving |  | Not Run |  |  |  | New Oct 15
ADM-44 | Admissions | Enrol - section | Functional | High | Admin | Application registered for 'Class 1' | Click Enrol; the Class list shows every section; pick Class 1 B; enrol | Sections are listed (Class 1 A, 1 B); the student is placed in the section you chose |  | Not Run |  |  |  | New Oct 15
ADM-45 | Admissions | Register - guardian mobile | Validation | Medium | Admin | None | Add a guardian with a name but no mobile; Save | Mobile has a red star; error 'Mobile is required.'; saves once the mobile is filled (not needed when an existing parent is picked) |  | Not Run |  |  |  | New Oct 15
ADM-46 | Admissions | Register - hints | UI | Low | Admin | None | Read the Remarks and Documents sections of New Registration | Remarks says it is an internal note for the office; Documents says no document is needed to register and that the Type of each file is picked from the list |  | Not Run |  |  |  | New Oct 15
STU-47 | Students | Citizenship | Functional | Medium | Admin | Existing student with an old free-text nationality | Edit > Citizenship | Nationality is a searchable dropdown (Indian and Emirati first); the old value is still shown and kept; there is no 'Second nationality' field |  | Not Run |  |  |  | New Oct 15
STU-48 | Students | Removed fields | UI | Low | Admin | None | Open a student's Edit and View pages and the list filters/export | No EAL code, no Second nationality, no Insurance provider/expiry, no English-level filter or EAL column in the CSV |  | Not Run |  |  |  | New Oct 15
STU-49 | Students | Left | Functional | High | Admin | Active student with a class period and attendance | Click 'Mark as left' (list row icon or the student's page) and confirm | Status becomes Left; the class history period closes as Left; the seat is freed; the student leaves the attendance roster; record and history remain; the button disappears |  | Not Run |  |  |  | New Oct 15
STU-50 | Students | Left - permission | Security | Medium | Clerk | None | Open Students and a student page | No 'Mark as left' action (needs Students.Edit); no Delete anywhere |  | Not Run |  |  |  | New Oct 15
STU-51 | Students | Left - twice | Negative | Low | Admin | Student already Left | Swagger: POST /api/students/{id}/leave again | 422 'This student has already left.'; nothing changes |  | Not Run |  |  |  | New Oct 15
PAR-17 | Parents | Delete - linked children | Negative | High | Admin | Parent linked to a student | Delete the parent | Refused: 'This parent is linked to N student(s). Unlink them first, then delete the parent.'; the parent still exists |  | Not Run |  |  |  | New Oct 15
PAR-18 | Parents | Delete - after unlink | Functional | High | Admin | Same parent as PAR-17 | Unlink every child (Linked children), then delete the parent | Delete now works |  | Not Run |  |  |  | New Oct 15
PAR-19 | Parents | Dropdowns and sections | UI | Medium | Admin | None | Add a parent; look at Country of residence, Preferred language and the sections | Country of residence offers India and United Arab Emirates; Preferred language includes Tamil; there is no 'Work & billing' section in the form, the details page or the header badges |  | Not Run |  |  |  | New Oct 15
ATT-26 | Attendance | Rules - 24 hours | Functional | High | Teacher | Class teacher; attendance saved for yesterday | Open yesterday and edit it; then open the day before yesterday | Yesterday and today are editable; the day before is locked ('Only an Admin can change attendance older than 1 day'); Admin can still edit it |  | Not Run |  |  |  | New Oct 15
ADM-47 | Admissions | Confirm - required payment | Validation | High | Admin | Registered application | Open Confirm Admission, leave Fee amount and Payment reference empty; click Confirm | Both fields show a red star and the errors 'Fee amount is required.' / 'Payment reference is required.'; nothing is saved; with both filled it moves to Admitted |  | Not Run |  |  |  | New Oct 16
ADM-48 | Admissions | Enrol - generated numbers | Functional | High | Admin | Two Admitted applications for the same section | Enrol the first with blank numbers, then the second | First gets ADM-<year>-0001-style and <class><section>001; second gets 0002 and 002; no gaps or duplicates; section A and B count separately |  | Not Run |  |  |  | New Oct 16
ADM-49 | Admissions | Enrol - typed number kept | Functional | Medium | Admin | Admitted application | Type your own roll and admission numbers and enrol | Your numbers are used as typed; the next blank enrolment continues after the highest serial |  | Not Run |  |  |  | New Oct 16
ADM-50 | Admissions | Register - document type first | UI | Medium | Admin | None | New Registration > Documents: look before choosing a type | A 'What are you uploading?' dropdown (searchable) is above the file picker, which says 'Choose a document type first' and is disabled until a type is chosen |  | Not Run |  |  |  | New Oct 16
STU-52 | Students | Labels | UI | Low | Admin | None | Check the Students list header, student pages, class page and parent page | The label is 'Adm No' everywhere (no 'Adm #') |  | Not Run |  |  |  | New Oct 16
STU-53 | Students | Photo upload | Functional | High | Admin | A student exists | Edit student > Basic: Upload photo, choose a JPG under 2 MB | The photo shows at once in the form and in the header of the student page; no Save needed |  | Not Run |  |  |  | New Oct 16
STU-54 | Students | Photo - wrong file | Validation | Medium | Admin | A student exists | Choose a PDF, a renamed .exe, and a JPG over 2 MB, one by one | Each is refused with a clear message (JPG or PNG only; size shown); the old photo stays |  | Not Run |  |  |  | New Oct 16
STU-55 | Students | Photo remove / replace | Functional | Medium | Admin | A student with a photo | Change photo to another picture; then Remove | The new picture replaces the old; after Remove the initials show again |  | Not Run |  |  |  | New Oct 16
USR-23 | Users & Staff | Employee number generated | Functional | Medium | Admin | None | Create a teacher and then a clerk, leaving Employee no. blank | They get EMP-0001 and EMP-0002; a typed number is kept; a duplicate is refused |  | Not Run |  |  |  | New Oct 16
LAY-10 | Login & Layout | No link underlines | UI | Low | Admin | Parents and Students lists | Look at names and mobile numbers, and hover over them | No underline anywhere, hovering included; links are still coloured and clickable |  | Not Run |  |  |  | New Oct 16
CLS-15 | Class Sections | Demo class set | Functional | Medium | Admin | After demo-reset and demo-seed | Open Classes | LKG, UKG and Class 1 to 5 each have sections A and B, every one with capacity 30 |  | Not Run |  |  |  | New Oct 16

## Test Data
Test data to set up first
Create these in a TEST database. Passwords are suggestions: change them if your policy differs (8+ characters, upper case, digit, special character).
Username | Role | Suggested password | Notes
admin | Admin | (existing admin) | Full access. Use for most cases.
admin2 | Admin | ZtAdmin#2026 | Second Admin: needed for document review (no self-review), concurrency and 'last Admin' cases.
zt.clerk | Clerk | ZtClerk#2026 | Limited role. Used for permission and masking cases.
zt.supervisor | Supervisor | ZtSuper#2026 | Limited role; can see identity values.
zt.teacher1 | Teacher | ZtTeach#2026 | Class teacher of 'ZT Class A' (assign it in Teachers). Used for attendance and scoped-access cases.
zt.custom | Custom role 'ZT NoParents' | ZtCustom#2026 | Create a role with Admissions.Create/Edit but WITHOUT Parents.View (cases ADM-G09, G10). Also create 'ZT ParentsOnly' with Parents.View but no Admissions rights (ADM-G11).
Sample records
Record | Name / value | Details | Notes
Class | ZT Class A | Section A, Primary, English, General, capacity 30 | Second class: ZT Class B. For 'full' tests make one with capacity 1.
Subject | ZT Math | Class A, Theory, max 100, pass 35
Parent | ZT Father | Mobile 9876501111 | Used in E2E-01, E2E-06 and the existing-parent cases.
Parent | ZT Mother | Mobile 9876502222
Applicant | ZTKid One | DOB a valid past date, Class A | Guardians: Father (mobile 9876501111) and Mother.
Documents | small.pdf, photo.jpg, scan.png | Any small files | Also: a text file renamed .pdf (must be refused) and a file over 5 MB.
Time | Test around midnight | 00:00-04:00 Abu Dhabi | For case ATT-25 only.

## Defect Log
Defect Log
One row per defect. Row 5 is an EXAMPLE (not counted in the Summary) showing the expected level of detail: overwrite or delete it. Copy the Defect ID into the failing test row. | [10 empty] | Severity: Critical = data loss / security / cannot continue; High = core feature broken; Medium = workaround exists; Low = cosmetic.
Defect ID | Date Found | Module | Test ID | Summary (one line) | Steps to reproduce | Expected vs Actual | Severity | Status | Reported By | Screenshot / File | Developer Notes
DEF-001 | 2026-10-15 | Students | STU-25 | EXAMPLE: Moving a student to another class does not add a history row | 1. Login as Admin 2. Students > Edit 'ZTKid One' 3. Change class A to B, Save 4. Open Academic History | Expected: two rows (Transferred + Active). Actual: one row only. Console shows no error. | High | New | Tester name | screenshot-001.png